Big Bend Continuum of Care

HMIS Committee Meeting

June 10, 2026  |  10:00 AM – 11:00 AM

Virtual Meeting  |  Teams Link: Click here to join

Welcome Back - Recommitting to Regular HMIS Committee Meetings This meeting marks our return to regular, bi-monthly HMIS Committee meetings after a pause earlier this year. Going forward, meetings are scheduled every other month. HMIS Committee meetings are open to all CoC partners, stakeholders, and community members with an interest in data-driven approaches to homelessness.

Coming July 2026 - Coordinated Entry Committee Meetings We are launching a dedicated Coordinated Entry (CE) Committee starting July 2026, meeting bi-monthly. CE Committee meetings will focus on policy, assessor training, referral workflows, and system performance. Watch for your calendar invite and additional details coming soon.

Meeting Agenda

| # | Agenda Item | Lead / Speaker |
| --- | --- | --- |
| 1 | Welcome and Introductions | Eric Layton |
| 2 | Roll Call and Quorum Confirmation | Committee Chair |
| 3 | HMIS Referrals Reintroduction - Project Status Update | Broderick Seabrooks |
| 4 | Coordinated Entry Revamp: Timeline and System Preview | Rachel Jeune |
| 5 | CE Committee Launch Announcement (Starting July 2026) | Rachel Jeune |
| 6 | HMIS Training Website Relaunch Announcement | Eric Layton |
| 7 | Housing Inventory Count (HIC) Quarterly Bed Inventory Surveys | Eric Layton |
| 8 | Data Quality Reminder: Updates & Annual Assessments | Broderick Seabrooks |
| 9 | Open Discussion / Agency Questions and Updates | All |
| 10 | Wrap-Up, Action Items, and Next Meeting Date | Committee Chair |

Discussion Details

Item 3 - HMIS Referrals Reintroduction

- Targeting August 1, 2026 soft launch with October 1, 2026 go-live

- WellSky configuration work underway - Broderick Seabrooks leading system build

- Beta testing phase to begin once configuration milestone is complete

- Agencies will receive updated guidance materials ahead of launch

Item 4 - Coordinated Entry Revamp

- CE Policies and Procedures draft in final review against HUD CPD-17-01

- Four-phase project plan with August 1 soft launch and October 1 go-live targets

- CE Specialist Rachel Jeune leading the assessment workflow and policy buildout

- Required components: appeals process, and annual CE assessor training

Item 6 - HMIS Training Website Relaunch

- Rebuilt role-based training ecosystem for intake staff, case managers, and agency leaders

- Mid-video quiz gating and custom learning paths now supported

- Agency Admin Training companion materials updated and available

- Rollout timeline and access instructions to be shared with participating agencies

Item 7 - Housing Inventory Count: Quarterly Bed Inventory Surveys

- Starting October 1, 2026, BBCoC will shift from annual to quarterly bed inventory reporting

- Agencies will survey and report bed inventory data four times per year

- This change improves the accuracy and timeliness of our Housing Inventory Count

- More information on reporting format, deadlines, and submission process coming ahead of October 1

Item 8 - Data Quality Reminder: Updates and Annual Assessments

- Document any client changes (income, insurance, disabilities, other SPM4 subassessment elements) in HMIS promptly

- These updates directly affect how we measure client outcomes and system performance

- Clients enrolled in a program for one year or more require an annual assessment, regardless of changes

- Annual assessments must be recorded on or before the client’s program entry anniversary date

Action Items

| Action Item | Assigned To | Due Date |
| --- | --- | --- |

Next HMIS Committee Meeting Date: August 5, 2026 @ 10am Eastern Time Please submit agenda items or questions to Eric Layton at least one week prior to the meeting.

Big Bend Continuum of Care  |  HMIS & Data Committee  |  Tallahassee, Florida